## Light
PROJECT:lookapp
Blackbear Technologies Inc. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Francis Chong
Project start date: | 2024-12-30 |  |  |  |  | January | [27 empty] | February
Scrolling increment: | 5 | time axis 2025-01-04 to 2025-02-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-01-04 to 2025-02-28
Sign-in/Sign-up Page
Basic HTML and CSS Designs | Milestone | Francis | 100% | 2024-12-30 | 1
Sign-Up Page and Functionality
Log-in Page and Functionality
Google and Facebook Redirects
Sign-Up Information Storage
Index or Landing
Basic HTML and CSS Designs | Milestone | Francis | 100% | 2025-01-07 | 1 | bar: 2025-01-07
Elements
Eyeglasses needs to be added into the text for logo
app scripts needs to be added into this page.
CSS and Java Scripts for functionality.
Explore or Results Page
Basic HTML and CSS Designs | Milestone | Francis | 100% | 2025-01-07 | 1 | bar: 2025-01-07
App scripts and functionality
Historical searches needs to be displayed as a drop-down. |  |  | 100%
search is triggered by hitting enter and click search.
search icon is too dark. |  |  | 100%
categories or filter button needs to be added.
Item detail page or item overview
tabs for functions
traffic lights
4 boxes for figures
hit request button for escalation
Request Page
Subscribe to Alerts
Support Page